## Sheet1
ERROR LOG
Defect No. | Date Created | Created By | Defect Description | Lifecycle Phase | Resolution Date | Time to Fix
1 | 2019-03-14 | Haresh | Dashboard created without bootstarp and front-end behaviour | Development | 2019-03-14 | 1 Hour
2 | 2019-03-15 | Haresh | Login and Register page, colours were mismatched | Development | 2019-03-15 | 10 Minutes
3 | 2019-03-17 | Akshay | Edit Test page was not responsive, nither looked good | Development | 2019-03-17 | 1 Hour
4 | 2019-03-21 | Mohit/Vishal | Add questions page was not responsive, nither looked good | Development | 2019-03-21 | 1 Hour
5 | 2019-03-30 | Riya | Examiner Dashboard Cards not working | Development | 2019-03-30 | 1.5 Hours
6 | 2019-04-02 | Vishal | Edit questions feature was buggy | Development | 2019-04-02 | 1 Hour
7 | 2019-04-08 | Akshay | Test Id was not genrated with a particular random pattern | Development | 2019-04-08 | 3 Hours
8 | 2019-04-09 | Akshay | The cards in student dashboard were not in chronological order | Development | 2019-04-09 | 4 Hours
9 | 2019-04-10 | Akshay | Start test button was not working | Development | 2019-04-10 | 1.5 Hours
10 | 2019-04-11 | Ankit/Pratibha | Issues with design on homepage | Development | 2019-04-13 | 2 Days
11 | 2019-04-12 | Mohit/Vishal | Selected options were not saved in the exam paper | Development | 2019-04-12 | 6 Hours
12 | 2019-04-13 | Soniya | Graphs not visible in view result page | Development | 2019-04-13 | 1 Hour
13 | 2019-04-13 | Soniya | Some pages had issues with responsivness | Development | 2019-04-13 | 2 Hours
14 | 2019-04-13 | Chirag | Issues with an API | Development | 2019-04-14 | 1 Day
15 | 2019-04-14 | Pratibha | Issues with details on footer | Development | 2019-04-14 | 1 Hour
16 | 2019-04-14 | Ankit | Issues with entire footer looks | Development | 2019-04-14 | 1 Hour
17 | 2019-04-14 | Ankit | Basic Visual issues with homepage | Development | 2019-04-14 | 2 Hours
18 | 2019-04-15 | Jaideep | Issues with documentation(SRS Questionnaire) | Documentation | 2019-04-15 | 1 Hour